## Sample Sheet
Action # | Issue/Action Item | Responsible | Decision-Maker (if applicable) | Assigned Date | Date Due | Status
1 | Agency has had difficulty fulfilling a data request by the SAO for [xxxx]. Agency and SAO need to reach agreement on what can be provided, by when. | [Name of Audit Liaison - who will determine with the division manager when/whether the request can be filled] | Not necessary at this time. Audit Liaison will act as decisionmaker unless the issue needs to be escalated. | 2006-08-07 | 8/11/2006 | Open - in progress 8/8/2006: Audit liaison spoke with assistant audit manager about agency constraints. Audit liaison will ask division whether parts of the data request can be filled within the timeframe, and when they expect to fulfill the entire request. 8/7/2006: Division manager raised concerns about being able to fulfill the request in the timeframe requested. The data is not readily available, and needs to be manually generated. In addition, the same people who need to compile the information are working on budget-related deadlines.
2
3
4
5

## Sample sheet with comments
Action # | Issue/Action Item | Responsible | Decision-Maker (if applicable) | Assigned Date | Date Due | Status
1 | Agency has had difficulty fulfilling a data request by the SAO for [xxxx]. Agency and SAO need to reach agreement on what can be provided, by when. | [Name of Audit Liaison - who will determine with the division manager when/whether the request can be filled] | Not necessary at this time. Audit Liaison will act as decisionmaker unless the issue needs to be escalated. | 2006-08-07 | 8/11/2006 | Open - in progress 8/8/2006: Audit liaison spoke with assistant audit manager about agency constraints. Audit liaison will ask division whether parts of the data request can be filled within the timeframe, and when they expect to fulfill the entire request. 8/7/2006: Division manager raised concerns about being able to fulfill the request in the timeframe requested. The data is not readily available, and needs to be manually generated. In addition, the same people who need to compile the information are working on budget-related deadlines.
2
3
4
5
Objectively state the issue, and what the desired outcome is (e.g., agreement on xx, fulfillment of data request by x/x/xx).
This person is responsible for identifying issues, assigning for resolution, monitoring for completion, and closing issues.
The decisionmaker will typically be the audit liaison when issues are being resolved at the lower levels in the agency. Change this column if the issue is escalated to the deputy, etc.
This is the date the decision needs to be made or resolution is expected. In this case, it would not necessarily be the due date requested by the SAO for the data request.
Note whether the issue is open or closed. Document the agency's action with whom and when. This column provides an important trail if the issue needs to be escalated for resolution.